PIP QI Measure 8

# Increase the proportion of patients with the necessary risk factors assessed to enable CVD assessment

First steps

- Nominate a lead person for this activity

- Use POLAR or refer to your POLAR practice report to identify your current percentage (your baseline) and decide on your target (%). Write it in Goal below.

- Decide how you will communicate with your practice team and patients about the improvement you’re working on.

- Refer to our quick guide for more ideas to increase the success of your improvement activity.

- Check the relevant HealthPathway for this condition to ensure your team is up to date with best practice management guidelines.

Setting up your QI activity and PDSA

| Goal | What are we trying to accomplish? By when? |
| --- | --- |
|  | Increase the percentage of Indigenous patients 35–80 and non-Indigenous patients 45–75 with cardiovascular risk factors recorded by [date] _________. Our target is _____%. |
| Measure | How will we measure this? |
|  | POLAR measure: The percentage of Indigenous patients aged 35 to 80 years and non-Indigenous patients aged 45 to 75 years with the necessary risk factors assessed in the past 2 years to enable CVD risk assessment. These risk factors include: - smoking status - diabetes (diagnosis on file or FBG/ HbA1C test result on file) - systolic blood pressure - total cholesterol and HDL cholesterol levels - age - sex. |
| Improvement ideas | - Use PIP QI Report in POLAR to pull the list of patients who are missing recording of cardiovascular risk factors. If you have a lot of patients identified, you could consider targeting one group at a time. - Decide how you will recall the patients on the list (for example: phone call, SMS, email or letter), how you will invite them in for care (what you will say) and how you will divide the tasks. Tip: If the list of identified patients is larger start with a smaller cohort of patients, such as calling the patients on one page per week, so you can review and modify your strategy as you go if needed. - You could identify gaps in cardiovascular risk factor recording on an opportunistic basis, or consider inviting patients for a 'Heart Health Check’ in line with the MBS item 699 descriptor. - Use QIPC Report - CVD Module in POLAR to identify harder to reach groups in your clinic (such as people from Aboriginal and Torres Strait Islander backgrounds) and have a staff member invite them by phone. Tip: Contact your NWMPHN Primary Care Facilitator if you need assistance to find these patients in your medical software. - Add an action prompt at an agreed place on the clinical software to alert clinicians to assess the missing risk factors |

| PLAN | Identify who will do each step, how they will do it and by when. Plan the activity, including a plan for collecting data. |
| --- | --- |

| Step 1 | Who will do this? | By when? |
| --- | --- | --- |
| Step 2 | Who will do this? | By when? |
| Step 3 | Who will do this? | By when? |
| Add more steps as needed. |  |  |

| DO | Who is going to do what? Run the activity on a small scale. Carry out the plan. Record data. Record any unexpected outcomes. |
| --- | --- |

When we looked at our baseline data, we found ______% of our practice’s Indigenous patients aged 35–80 and non-Indigenous patients aged 45–75 had cardiovascular risk factors recorded.

What we did:

By [insert the date stated in Goal section] _______, [insert number] _______% of our practice’s Indigenous patients aged 35–80 and non-Indigenous patients aged 45–75 had cardiovascular risk factors recorded.

Unexpected outcomes:

| STUDY | Analyse the results and compare them to your predictions. Does the data show a change? |
| --- | --- |

Write your responses to the following questions to reflect on your activity and what you learned.

Did you achieve what you thought you would? Did your strategy work well? If yes, why? If no, what needs to be changed? What challenges or barriers occurred?

| ACT | Do you need to make changes to your original plan? Based on what you learned from the activity, plan for your next step. |
| --- | --- |

What next? Will you implement the change or try something new? What idea will you test next? What will you take forward; what is the next step or cycle?

What will you do now? Will you continue with the activity, change or improve it? Does this activity need to be repeated in the future? Could a reminder be scheduled for this? What improvement activity will your team focus on next?

Next steps

Try out another QI activity

After completing this activity, you may wish to consider another QI activity:

- PIP QI Measure 10: Improve blood pressure recording for patients with diabetes

- PIP QI Measure 1: Improve HbA1C recording in your practice

- PIP QI Measure 3: Increase BMI recording in your practice

- PIP QI Measure 9: Increase cervical screening rates in your practice

Visit nwmphn.org.au/qi to download templates for these activities.

Celebrate your work

We would love to publish your quality improvement story on our website and share it with other practices. We encourage you to share your completed template and any photos from the project with us.

If you would like to tell us about your outcomes, please contact primarycare@nwmphn.org.au

Support

If you need any support to implement your activity, if you had any difficulties, please contact us. Email primarycare@nwmphn.org.au or call (03) 9347 1188 to speak to your practice’s quality improvement program officer.